## Start Here
Instructions: Complete the following fields. The spreadsheet will then populate the other sheets of this workbook
Client Name | Ojai Valley Inn & Spa
Project Start Date | 2012-01-05 | Be sure to review populated dates on timeline sheet
2011 Holidays (Affect Timeline)
| New Year's Eve | 2011-12-31
| New Year's Day | 2011-01-01
| Memorial Day | 2011-05-31
| Independence Day | 2011-07-04
| Labor Day | 2011-09-06
| Thanksgiving | 2011-11-25
| Day After Thanksgiving | 2011-11-26
| Christmas | 2011-12-25

## WebDev Timeline
Milestone | Expected Date | Completed | Difference | Internal/External | Dept
Signed SOW received from Ojai Valley Inn & Spa | 2012-01-05 |  |  | External | WebDev
SHS Begins Website Transfer | 2012-01-12
Performs Scrape of Ojai Websites
Moves Website Files to SHS Hosting Environment
Website Forms Rebuilt and Processed to Sabre Portal
Websites Reviewed and Tested
Ojai Valley Inn & Spa sends list of Vanity Domains to SHS | 2012-01-23 |  |  | External | WebDev
Ojai Valley Inn & Spa Initiates Domain and Vanity Domain Transfer to SHS | 2012-01-23
SHS Confirms Domain and Vanity Domain Control Transfer | 2012-01-25
Beta of Websites Delivered to Ojai Valley Inn & Spa | 2012-01-26
Client Approval of Beta Websites | 2012-01-27 |  |  | External | WebDev
Website Launch - Ojai Valley Inn & Spa | 2012-01-30 |  |  | External | WebDev
Website Launch - Casa Elar | 2012-01-31 |  |  | External | WebDev
|  |  |  | External | WebDev
|  |  |  | External | WebDev
|  |  |  | External | WebDev
|  |  |  | External | WebDev
|  |  |  | External | WebDev
|  |  |  | External | WebDev
|  |  |  | External | WebDev
|  |  |  | External | WebDev
|  |  |  | External | WebDev
|  |  |  | External | WebDev
|  |  |  | External | WebDev
|  |  |  | External | WebDev
|  |  |  | External | WebDev
|  |  |  | External | WebDev
|  |  |  | External | WebDev
|  |  |  | External | WebDev
|  |  |  | External | WebDev
Formulas:
Expected Date = WORKDAY([Expected Date, row above],2,0)
Expected Date = WORKDAY([Expected Date, row above],1,Holidays)